## minutes of meeting
Minutes of NAVOLCHI Meetings and Conference Calls
Meeting | Item No. | Contents | Type | Resp. | Concerning | Due date | Status | Result | Open issues | Close date
1 | 0 | Date: 03.02.2012 0900 - 1600 Title: Navolchi Kick-Off Meeting Consortium Institutions: KIT, IMEC, TU/E, AIT, UVEG, UGent, STi Institutions are represented by meeting members: (KIT) Prof. Juerg Leuthold, Dr. Manfred Kohl, Dr. Martin Sommer, Argishti Melikyan, Sascha Mühlbrandt (IMEC) Prof. Dries Van Thourhout (TU/E) Victor Dolores-Calzadilla (AIT) Dr. Emmanouil-Panagiotis Fitrakis (UVEG) Prof. Juan Martinez Pastor, Dr. Isaac Suárez Alvarez, Dr. Pedro Rodriguez-Cantó (UGent) Prof. Hens Zeger, Pieter Geiregat, Yolanda Justo (STi) Alberto Scandurra not present due to illness) | I
1 | 1 | Voting Power | D
|  | Voting power has been assigned to the following members of the respective institutions. Each insitution contributes with a single vote. (TU/E) Smith (AIT) Tomkos (IMEC) Van Thourhout (UGent) Zeger (KIT) Leuthold (STi) Scandurra | D
1 | 2 | Introduction by J. Leuthold & Review of Project Administration | I |  | all
|  | Presentation of host KIT & IPQ/IMT | I
|  | Navolchi Requirements, Budgeting, Manpower | I
|  | Review of Navolchi technical objectives, deliverables and timescales. Reference to Project Website www.Navolchi.eu for Project related documents and publications | I
1 | 3 | Election of Technical Project Manager | D |  | all
5 present voting members voted for Manfred Kohl (KIT) as Technical Project Manager
1 | 4 | Discussion of the Project Programme / Agreements | I |  | all
|  | J. Leuthold (KIT) proposes change of Consortium agreement with respect to paragraph 8.3.1.1: "The time limit in which objections to publications have to be claimed is decreased from thirty (30) days to seven (7) days." 5 present Voting Members vote for proposal. Proposal accepted. | D |  | all
|  | Meeting members agree to allocate conference calls for every first Monday of a month, 4 pm Conference phone number available on Navolchi website. Exception needed for March 2012 due to overlap with OFC. Next conference call will be on March,12th 2012 4 pm. | D |  | all
|  | Meeting members agree to allocate next Consortium meeting for first week of July, 2012. Possible locations are either Gent/Belgium or ICTON2012 (UK) Conference. Exact date and location to be determined with a "Doodle"-Request. | D | Sommer | all
|  | It has been agreed with Coordinator and Partners that there will be at least 1 IMEC run a year (Van Thourhout (IMEC) states there are 2 epixfab runs a year, but recomends IMEC run i.e. one of the (not LETI)) | D
1 | 5 | Technical Presentations
|  | (UVEG) J. Martinez: Plasmonic Amplifier, Detector | I |  | WP
|  | (IMEC) Van Thourhout, Geiregat: Transmitter, Amplifier for Receiver, Interfaces | I
|  | (KIT) Melikyan: Plasmonic Modulator, Photodetector Design, Plasmonic Couplers | I
|  | (UGent) Zeger: Quantum-Dot Amplifier | I
|  | (AIT) Fitrakis: Simulation and Modeling of Plasmonic Amplifier, Organiziation of Navolchi-Session at ICTON2012 | I
|  | (TU/E) Calzadilla: Plasmonic Laser Review and Optimization of Bonding Technology | I
|  | (STi) presented by Kohl (KIT): CMOS to Plasmonic Interface Design | I
1 | 6 | Outstanding Technical Issues
|  | Leuthold (KIT) remarks all system components (Modulator, Amplifier, Detector) are still being developed and need to be optimized. Therefore interconnect solutions can not be defined before single components. Asks for a dense cooperation to achieve compatible devices. |  |  | WP3, WP4, WP5
|  | Quantum-dot Amplifiers are set up to work in visible regime. Leuthold (KIT) proposes to shift wavelength to the telecommunication regime when Si-based interconnects shall be used to prevent losses. Partners associated with Quantum-Dot technology point out that utilized wavelength can be adjusted. |  |  | WP5
|  | Coupling of Plasmonic Laser to Waveguide (WG) needs to be defined. Dolores-Calzadilla (TU/E) proposes to couple from Plasmonic Laser to Si-WG via intermediate tapered InP-WG overlapping a tapered Si-WG, because TU/E`s technology so far is based on emission into InP-WG. Leuthold (KIT) adresses probable high losses due to modal mismatch and proposes to directly place Plasmonic Laser on grating coupler on a Si-WG to outcouple. Melikyan (KIT) proposes bonding of InP substrate. Fabrication of Plasmonic Laser already bonded InP on SOI. |  |  | WP3
1 | 7 | Upcoming Workpackages / Deliverables / Milestones (Discussion)
|  | According to schedule STi needs to finish Deliverable 5.1 (Dual Dice Communication Module specification) in 2 months. Exact progress unclear and needs to be determined. Sommer (KIT) will get in touch with STi. |  | Scandurra | WP5
|  | Fitrakis (AIT) proposes a Navolchi-Session at ICTON2012 in fulfillment of WP7. Leuthold (KIT) doubts that there are already suitable Navolchi publications present and proposes to submit Navolchi-related pre-existing Consortium technology instead. |  |  | WP7