## minutes of meeting
Minutes of NAVOLCHI Meetings and Conference Calls
Meeting | Item No. | Contents | Type | Resp. | Concerning | Due date | Status | Result | Open issues | Close date
3 | 0 | Date: 25.11.2012 1000 - 1700 Title: Navolchi Meeting Gent Consortium Institutions: KIT, IMEC, TU/E, AIT, UVEG, UGent, STi Institutions are represented by meeting members: (KIT) Prof. Juerg Leuthold, Dr. Manfred Kohl, Argishti Melikyan, Sascha Mühlbrandt (IMEC) Prof. Dries Van Thourhout (TU/E) Victor Dolores-Calzadilla (AIT) Dr. Emmanouil-Panagiotis Fitrakis (UVEG) Prof. Juan Martinez Pastor, Dr. Isaac Suárez Alvarez (UGent) Prof. Hens Zeger ((STi) Alberto Scandurra | I
| 1 | Technical presentations
Each WP leader gives the technical presentation dedicated to the review meeting. Each presentation is organized in a coherent common shape
(KIT) Coordinator Talk
(AIT) WP2
(TU/e) WP3
(UVEG) WP4
(IMEC) WP5
(ST) WP6
(AIT) WP7
(KIT) WP1
| 2 | NAVOLCHI summer schools, courses
The consortium has to organize a summer school in the context of NAVOLCHI. The partners are asked to look for for similar courses in their institutions where NAVOLCHI could participate.
| 4 | Discussion about system approach and contingency plan
Prof. Leuthold suggests realizing a system approach as given in the graph below. No partner expressed objections to this suggestion.