## minutes of meeting
Minutes of NAVOLCHI Meetings and Conference Calls
Meeting | Item No. | Contents | Type | Resp. | Concerning | Due date | Status | Result | Open issues | Close date
5 | 0 | Date: 26.04.2013 0900 - 1600 Title: Navolchi Meetingn 05, Karlsruhe Consortium Institutions: KIT, IMEC, TU/E, AIT, UVEG, UGent, STi Institutions are represented by meeting members: (KIT/ETH) Prof. Juerg Leuthold, Dr. Manfred Kohl, Dr. Martin Sommer, Argishti Melikyan, Dr. Yuriy Fedoryshyn, Claudia Hößbacher, Sascha Mühlbrandt (IMEC) Prof. Dries Van Thourhout (TU/E) Victor Dolores-Calzadilla (AIT) Dr. Emmanouil-Panagiotis Fitrakis (UVEG) Dr. Isaac Suárez Alvarez (UGent) (STi) Alberto Scandurra
| 1 | Introduction
/
| 2 | Preparation for Brussels meeting July '13
Open Milestones and Deliverables: Reminder to finish them before meeting
Adminstrative: Finances, man power and summary of WP need to be prepared
Phone conferences until July meeting: May 13th, May 27th (optional), June 10th, July 1st, July 10th
| 3 | Technical Presentations
1.) AM for KIT: Plasmonic Phase Modulator - Question for ST: What are the critical numbers for the BER, that electronics can cope with? - JL: Taper coupling losses should be decreased to less than 1dB per coupler - AM: Less than 10dB losses should be possible in the slot - All: For Brussels meeting, all options for the system should be pointed out, e.g. (phase-modulator, absorption modulator, directly modulated nanolaser) could each be combhined with (plasmonic photo detector, avalanche photodiode) - Questions from EPF: Why is the phase modulator not smaller (length), e.g. comparable to the wavelength? Reviewers might pose that question. Answers will be prepared - DVT: High-Q resonator + detector might be available from IMEC as a further option for the system (avoids Mach Zehnder configuration) - AM to DVT: When will a new run at IMEC be possible? -> No run currectly going on, but will check when new run is available
EPF for AIT: System specs and Brussels meeting preparation - System specifications: What will be sizes of the chip, as this will be compared to other silicon chips - State of the art of Electronics/Photonics/NAVOLCHI/Future should be mentioned. References need to be given when numbers are stated - AIT reminds partners to comment on recent achievements and exploitation activities, which are needed for D7.2, D7.4 Discussion of Reviewer's comments: Comments II: Figures will be supplied by AM, draft by EPF Comments III: System integration of devices - ST will write AIT about the expected potential of cointegration of electronics and plasmonics Comments IV: Complete device and system specs JL: KIT will perform simulations on electrical crosstalk, Tu/e will look into thermal effects
AS for ST: Electrical interface, adapters and speed limitations - MS4 will be finished within two weeks - higher driving voltages would mean faster signals for devices, driver is limiting speed of electrical interface - Maximum speed of driver: 4Gbit/s
VC for Tu/e: Metallo-Dielectric Nanolaser - Outcoupling of laser to Silicon wavegudie or grating - MS13 and MS15 will be merged AND MS15 needs then to be postponed to February 2014 (Last item needs to be decided) - Planned output power level is unlikely to be achievable, will aim for 50µW instead - Answer to laser-specific Reviewer's comments, thickness of metal will be below 1µm, relevant parasitics are thermal in nature
IS for UVEG: Plasmonic Detector and Amplifier MS20 will be finished with approximately 3 weeks delay
DVT for IMEC and Ugent - Issue with pitch of grating coupler, long distances between chips not possible. Solution might be focused gratings - Grating pitch will be re-defined when solution is found or distance between chips will be reduced - JL: Modulator and gratings will be on the same chips, so they must be on the same masks - New backup photo detectors given to Claudia Hößbacher
| 4 | Further Technical Issues
Electronic Interface - Interface between electronics and plasmonic devices: Board is needed and must be defined, electronic pitch is needed to be known - 7.2Gbit/s is possible for link with 16 channels, 450MHz per channel due to limitations of electronics
To overcome limit of electronics two systems should be persued: - Project demonstrator as given in the DoW, but limited by electronics - A fast physical link comprising the plasmonic devices and external driving electronics to demonstrate potential of the NAVOLCHI approach