## minutes of meeting
Minutes of NAVOLCHI Meetings and Conference Calls
Phone Conference | Item No. | Contents | Type | Resp. | Concerning | Due date | Status | Result | Open issues | Close date
XX | 0 | Date: 28.01.2014 Title: Navolchi project meeting Eindhoven Consortium Institutions: Institutions are represented by: (KIT) Prof. Juerg Leuthold, Dr. Manfred Kohl, Argisthi Melikyan, Claudia Hoessbacher (IMEC) - (TU/E) Prof. Meint Smit, Victor Dolores-Calzadilla, Dr. Domiminik Heiss (AIT) Christoforos Kachris (UVEG) Dr. Isaac Suárez Álvarez (UGent) Prof. Zeger Hens (ST) Alberto Scandurra | I
| 1 | New person from AIT (Christoforos Kachris, Emanuel has left) | I
| 2 | ST pulls back from WP6 (22 MM), has to be moved to another partner (see also item No. 6, ST) | I
| 3 | Decision on final demonstrator needed, several options, contingency plan: external laser + IMEC Si-Ge PD (see also Item No. 7) | I
| 4 | reviewer's comment: system level planning needs improvement (D1.5 and M39, D6.3) | I
| 5 | 6 Milestones and 5 deliverables delayed, intermediate progress report coming up
|  | MS22 integrated ampflifier not possible at the moment, amplification with HgTe demonstrated; | I | IMEC
|  | MS15 and corresponding deliverable(D3.3) can be submitted, frist fabrication run completed, next run started | I | TU/e
|  | MS23 close, but target not yet achieved, report will be written |  | UVEG
|  | MS33: Manfred Kohl will contact Dries Van Thourhout |  | IMEC
|  | MS34: document is currently completed |  | ST
|  | MS38: in progress |  | KIT
|  | MS39: will be discussed later today |  | AIT
|  | D2.3: is ready, can be submitted today |  | AIT
|  | D3.4: in progress |  | KIT
|  | D3.3: can be submitted |  | TU/e
|  | D5.4: in progress |  | ST
|  | D5.5: almost done |  | IMEC/KIT
D1.5: intermediate progress report due 01/2014
| 6 | Technical discussion of the work packages
|  | Plasmonic waveguide coupler optimized in simulations |  | KIT
Plasmonic phase modulator (SPPPM) fabricated and characterized, 40 Gbit/s demontrated with BER 6*10^(-5), MZM design submitted to IMEC (will be received in February), array with channel spacing 50 µm and 35 µm, no 250 µm pitch due to space constriants
Plasmonic absorption modulator (SPPAM) fabricated and characterized, high ER but low speed, array with channels spacing 35 µm, 50 µm and 250 µm
|  | laser: first fabrication run completed, but process (mainly bonding) needs improvement, next run planned which may include array |  | Tu/e
cooperation with UVEG for fabrication of the detectors
|  | digital building blocks and interconnect models are completed |  | ST
reorganization within ST ---> digiltal blocks (FPGA implementation) can be implemented, but analog blocks (board design, driver etc.) has to be moved to another partner, FPGA of ST cannot be shipped, so the partner has to provide an FPGA. That means that WP6 (22 MM) has to skipped by ST, but all other WPs can be carried out
|  | amplification with HgTe quantum dots demonstrated, next step transfer from solution to thin films for integrated amplifier |  | UGent
|  | in contact with UGent for integrated amplifier design with HgTe QDs, plasmonic waveguides characterized, in contact with Tu/e for fabrication of nanogap photodetector |  | UVEG
|  | system level simmulations for scenarios for transmitter side: 1) external laser and a) SPPAM or b) SPPPM 2) direct modulated plasmonic laser |  | AIT
scenarios for receiver side: 1) plasmonic photo detector from UVEG 2) standard PD from IMEC; both with and without amplier
| 7 | Scenarios for the final demonstrator
Jürg Leuthold: 1) external laser, split into 4 channels, SPPAM or SPPPM, (external amplfiication and filter), PDs from IMEC
2) direct modulated laser of 4 channels, (external amplfiication and filter), PDs from IMEC
| 8 | project needs extenction of 6 months |  | KIT
officiers will be informed (end of February) that the pending milestones and deliverables will be submitted soon, propose new schedule and ask for an extenction of 6 months, since fabrication has been done in time, but outcome reuqires additional fabrication runs
all partners must confirm and give reasons for the delay (1/2 page) until first week of February to Manfred Kohl or Matrin Sommer
TU/e and KIT: first fabrication runs indicate that new fabricaion runs are needed to deliver better results + problems with machines cause delay of fabrication
ST: reorganization --> WP6 needs to be moved to another partner
UVEG: specs not yet met