## minutes of meeting
Minutes of NAVOLCHI Meetings and Conference Calls
Phone Conference | Item No. | Contents | Type | Resp. | Concerning | Due date | Status | Result | Open issues | Close date
6 | 0 | Date: 04.06.2012 4pm Title: Navolchi Telephone Conference 06 Consortium Institutions: KIT, IMEC, TU/E, AIT, UVEG, UGent, ST Institutions are represented by: (KIT) Dr. Martin Sommer, Argishti Melikyan, Sascha Mühlbrandt (IMEC) Prof. Dries Van Thourhout (TU/E) Victor Dolores-Calzadilla (AIT) Dr. Emmanouil-Panagiotis Fitrakis (UVEG) Prof. Juan Martinez Pastor, Dr. Isaac Suárez Álvarez (UGent) (ST) Alberto Scandurra | I
| 1 | Progress Reports | I
KIT: Device fabrication of Plasmonic Modulator; Device transmission and poling; Current activities; NAVOLCHI on IMEC10 without protective resist, possibly damaged
TU/e: Deliverable3.1:Optimized structure; Coupling; Modal distribution; Confinement factor; Influence of device dimensions; Reflectivity and outcoupling; Threshold gain and initial efficiency; Alternative structure with dielectric modes Milestone 8 will be finished soon
AIT: Symmetric vs. Asymmetric Waveguide; White Paper for innovation and technology transfer: Invites Partners to contribute; MS2 is submitted Information on ICTON2012 see respective section below
UVEG: Dielectric and Plasmonic CdSe-PMMA waveguides
IMEC/UGent Characterization of Qdots interaction with silicon waveguide; Building amplifier structure; New gain characterization in cooperation with TU Delft; From Ugent: Currently preparing new Qdots for Valencia
ST: DDCM design activity in progress Subgroup STG will leave project after year one
| 2 | ICTON 2012 Navolchi Session and Consortium Meeting | I
NAVOLCHI Session @ ICTON2012 will be held on Thursday, July the 5th 09.30 - 12.00. NAVOLCHI Consortium Meeting will take place on Friday, July the 6th 09.00 - 17.00. Emmanouil Fitrakis(AIT) awaits input from every Partner about how many people will attend Payment: - Every participant pays for his own expanses from his respective budget - Common expanses (deposits and alike) are shared between partners, Holger Moritz(KIT) is to be asked how these can be regulated.
| 3 | Reminder: Intermediate Progress Report July 2012 | I
Input from every partner needs to be filed in JUNE 2012
| 4 | Next regular Telephone Conference | I
If Phone Conference will take place to be clearified due to Consortium Meeting the same week. If it takes place, appointment will be Monday, July the 2th, 4pm