## minutes of meeting
Minutes of NAVOLCHI Meetings and Conference Calls
Phone Conference | Item No. | Contents | Type | Resp. | Concerning | Due date | Status | Result | Open issues | Close date
12 | 0 | Date: 14.01.13 4pm Title: Navolchi Telephone Conference 12 Consortium Institutions: KIT, IMEC, TU/E, AIT, UVEG, UGent, ST Institutions are represented by: (KIT) Dr. Martin Sommer, Dr Manfred Kohl Argishti Melikyan, Sascha Mühlbrandt (IMEC) Prof. Dries Van Thourhout (TU/E) Victor Dolores-Calzadilla (AIT) Dr. Emmanouil-Panagiotis Fitrakis (UVEG) Dr. Isaac Suárez Álvarez (UGent) Prof. Zeger Hens (ST) Alberto Scandurra | I
| 1 | Progress Reports | I
Reports available on NAVOLCHI website
| 2 | Discussion about review meeting in Brussels | I
Report from Reviewers arrived, AIT has open questions with respect to answers to reviewers: - InP on Si: limit of integration? - Thermal effects and crosstalk expectations for NAVOLCHI system
| 3 | Upcoming Consortium Meeting | I
Planned to have consortium meeting middle of April, one month later EC Review meeting: No partner objects
| 4 | Organizational matters
6 Milestones due in January 6 Deliverables due in April Which partner is responsible for D7.1 and D7.3?
| 4 | Next Telephone Conference | I
February 4th, 2013 4pm