## minutes of meeting
Minutes of NAVOLCHI Meetings and Conference Calls
Phone Conference | Item No. | Contents | Type | Resp. | Concerning | Due date | Status | Result | Open issues | Close date
17 | 0 | Date: 17.06.13 4pm Title: Navolchi Telephone Conference 17 Consortium Institutions: KIT, IMEC, TU/E, AIT, UVEG, UGent, ST Institutions are represented by: (KIT) Dr. Martin Sommer, Dr Manfred Kohl, Sascha Mühlbrandt (IMEC) Prof. Dries Van Thourhout (TU/E) Victor Dolores-Calzadilla (AIT) Dr. Emmanouil-Panagiotis Fitrakis (UVEG) Dr. Isaac Suárez Álvarez (UGent) Prof. Zeger Hens (ST) Alberto Scandurra | I
| 1 | Progress Reports | I
Reports available on NAVOLCHI website
| 2 | First Periodic Report | I
AIT asks device leaders for input, needed for definition of system specs. Discussion about Reviewers comments on phase modulator. Discussion about AIT crosstalk input (Reviewer's comments)
KIT: Partners are asked to submit missing parts for the 18months Periodic Report, espacially the finacials (Form C)
Preparation meeting will be held on Tuesday, 9th july. Meeting room is Office of Helmholtz association, Rue du Trone 98, Brussels. Meeting starts 1.30pm
| 3 | Other | I
After restructuring of ST: Positive feedback for NAVOLCHi from new ST management. ST will employ new engineer on NAVOLCHI
| 4 | Next Telephone Conference
July 1st, 2013 4pm