## minutes of meeting
Minutes of NAVOLCHI Meetings and Conference Calls
Meeting | Item No. | Contents | Type | Resp. | Concerning | Due date | Status | Result | Open issues | Close date
2 | 0 | Date: 06.07.2012 0900 - 1415 Title: NAVOLCHI Meeting Warwick/UK Consortium Institutions: KIT, IMEC, TU/E, AIT, UVEG, UGent, STi Institutions are represented by meeting members: (KIT) Argishti Melikyan, Sascha Mühlbrandt (IMEC) Prof. Dries Van Thourhout (TU/E) Victor Dolores-Calzadilla (AIT) Prof. Ioannis Tomkos (UVEG) Dr. Isaac Suárez Alvarez (UGent) Prof. Zeger Hens (ST) Alberto Scandurra | I
| 1 | Project Administration Review (Argishti Melikyan) | I | KIT
Change in Project-Management-Commitee: Suárez(UVEG), Calzadilla(TU/e) and Melikyan(KIT) replace the respective members of the Project-Management-Commitee for this meeting.
All Milestones and Deliverables to date have been finished on time.
D1.4: Intermediate Progress Report needs to be filed end of July. ST, AIT, TU/e contribution is still missing. Input from each partner expcted 10th of July. Form C has to be filed by every beneficiary (see Grant Agreement Annex II: Paragraph II.4-1-C)
Next deadline for various upcoming Deliverables and Milestones is October 2012.
Status of Budget: No problems announced with respect to finances and personnel.
Suggestions to improve collaboration: - (Melikyan) Communication between partners and exchange of technical results and specifications can be improved - (Tomkos) Exchange of people between locations will improve cooperation on common WP
Currently no further critical technical issues differing from Description of Work. Tomkos: Plasmonic system to be developed in NAVOLCHI framework is most likely not able to beat current or alternative solutions. The respective statements of targetted performance in the Technical Annex should be proactively altered to less strict levels. Van Thourhout: Long-term performance of plasmonic systems can be expected. Proof-of-Principle No decision made.
Issues related to MS/D: - According to the Annex, for various Milestones the leading party is not the party that actually provides the technical work (e.g. WP3/MS10 "Grown wafer structure for plasmonic lasers" is lead by IMEC, but TU/e grows their wafers themselves). All MS and D should be revised for such inconsistencies and responsibility changed according to the respective provider of the work. Please inform Martin Sommer about inconsistencies! No decision made. - For some MS it would make sense to merge due to better fit to actual experimental proceeding (e.g. MS13: 'Initial characterization of unbonded plasmonic lasers' and MS15: 'Initial testing of bonded plasmonic lasers'). No decision made. - Inconsistency for some MS/D with respect to leading party between Proposal <-> DOW Annex <-> Project Website: The description as given in the Technical Annex holds. Inconsistencies between Annex and website will be checked. All Partners should inform Martin Sommer (KIT) about inconsistencies on the website.
Appointment for next convention needs to be found: Hosting partner, date and location.
Next Phone Conference: September 3rd 1600 - the phone conference in August will be skipped due to many participants being on vacation in the respective period.
| 2 | Technical Presentations (available on website) | I | ALL
AIT: Status of work at AIT; Simulations on symmetric and asymmetric plasmonic Waveguides; Investigation of loss and gain in plasmonic Waveguides AIT asks partners to provide input with respect to their publishing and dissemination plans! AIT asks for suggestions for possible locations of a NAVOLCHI summer school and a work shop in a new-member-state of the EU.
ST: Main achievements of ST; ST schedule is on time; STG leaves project end of the year; No results yet to be published, WP6 expects results after year 1;
UVEG: Amplifier gain in symmetric and asymmetric WG; Progress on Photodetector
Ugent: PbS/CdS Quantum Dots/Rods; Single/multiple Quantum Dots in Quantum rods; Absorption and decay channels in QD
IMEC: Integration of QD amplifiers into silicon WG; Passive Filters; Beam steerers
TU/e: Comparison of Plasmonic Laser and Metallo-Dielectric Laser with dielectric mode: Metallo-Dielectric Laser outperforms Plasmonic counterpart and should be chosen for fabrication. Technical Annex allows exploitation of both, Metallic or Plasmonic Laser. First fabricated device will not be available before 2013.
KIT: Simulation of Plasmonic Phase Modulator; Plasmonic Absorption Modulator as earlier proposed by the KIT might be appropriate solution for utilization in the project; Simulation on tapered coupling structure
| 3 | Further points discussed | D
Van Thourhout and Melikyan agree on additional IMEC run for the KIT's modulator.
Scandurra, Calzadilla and Melikyan agree that for the initial system demonstrator one plasmonic link is sufficient.
| 4 | Action-plan/near future achievements for the consortium as a whole | I
Finalising the Intermediate progress report and submission to the Commission.
If required revision and rearrangement of some MS and D.
Preliminary planning of the NAVOLCHI summer school and work shop in EU new-member-state.
Preperation of next NAVOLCHI convention