## Slide 1
Work Package 6 Presentation
Alberto Scandurra
STMicroelectronics, Italy

## Slide 2: Outline
WP6 Position in Project
Objectives
Tasks
Milestones and Deliverables
Status of Work
  Plasmonic/Metallic Laser
  Plasmonic Modulator
Summary and Outlook

## Slide 3: WP6 Position in Project
Contributors:

## Slide 4: Objectives
Validation the research activities carried out in the other WPs by means of a demonstrator implementing a simple System-in-Package exploiting all the developed building-blocks (plasmonic devices and digital/analog modules)

## Slide 5: Tasks
 | Names of the Tasks | Time Period [months]
T6.1 | Characterization of active and passive plasmonic devices | 7-33
T6.2 | Assembly and packaging of plasmonic devices into System in Package | 30-36
T6.3 | Plasmonic chip-to-chip interconnect prototype testing and evaluation | 32-36
T6.4 | System in Package integration and characterization | 22-36

## Slide 6: Milestones
 | Names of the Milestones | Month | Partner
MS37 | Plasmonic active device characterization results | 12 | AIT
MS38 | Plasmonic passive components characteriaztion results with a 1dB coupling loss | 24 | AIT
MS39 | Concept for system integration developed | 27 | AIT
MS40 | Individual plasmonic devices characterization, testing and evaluation | 30 | AIT
MS41 | Chip to chip interconnect characterization | 33 | ST
MS42 | Plasmonic components integration to demonstrate chip-to-chip interconnect | 33 | KIT
MS43 | Plasmonic chip-to-chip interconnect prototype testing and evaluation | 36 | ST

## Slide 7: Deliverables
 | Names of the Deliverables | Month | Partner
D6.1 | Report on characterization results of all plasmonic devices | 27 | AIT
D6.2 | Report on characterization results of all optical interface plasmonic passive components | 27 | AIT
D6.3 | Report on chip-to-chip interconnect characterization | 36 | ST
D6.4 | Report on plasmonic chip-to-chip interconnect prototype testing and evaluation | 36 | ST

## Slide 8
Got FPGA equipment for demonstrator (ZeBu)
  Managing up to 32 Mgates at the speed of up to 30 MHz
  Currently installed in ST Grenoble by verification/validation group
  NAVOLCHI activity starting remotely in a few weeks
  FPGA equipment planned to be moved to ST Catania beginnning of next year
Status of Work: Demonstrator
ZeBu
Design-Under-Test
(DUT)
Memory
Memory
Server
Clock
Server
FPGA
FPGA
FPGA
FPGA
FPGA
FPGA
FPGA
FPGA
PC / Linux
PCIe
I/F
Transaction-Based
Cycle-Based
Target System
Hard
Cores
Logic Tiles
DirectICE
Verilog/VHDL
SystemVerilog
C/C++
SystemC
Vectors
C/C++
SystemVerilog
SystemC
Reconfigurable
TestBench
(RTB)
TX
RX
Logic
Resources
Clock Trees
Memory
Resources
Memory
Memory
Memory
Software
Debuggers
Smart Z-ICE
Hardware Transactors
Embedded Testbench
Probes (Dyn./Flex/Stat.)
Triggers
Logic Analyzer
SVA’s
Live Real World
Testing

## Slide 9: Summary and Outlook
  Summary
    No deliverables expected during first year (first deliverables expected month 27)
  Outlook
  Modeling and fabrication of coupling Si waveguide to plasmonic waveguide
  Design and fabrication of Si beam shaper
  Design and fabrication of passive ultra-compact components and filters
  Signal generation module design