## Slide 1
Work Package 5 Presentation
Dries Van Thourhout
IMEC, Belgium

## Slide 2: WP3 Position in Project
Contributors:

## Slide 3: Objectives
Overall Objective :
Specific Objectives:
  Coupling light between silicon backbone and plasmonic devices
  Beam Shaping grating couplers to direct light between chips
  Compact filters for noise suppression
  Specify and implement Dual Die Communication Module (DDCM)
Design and implement optical and electrical interfaces for plasmonic interconnect

## Slide 4: Tasks
 | Names of the Tasks | Time Period [months]
Task 5.1 | Modeling and fabrication of coupling Si waveguide to plasmonic waveguide | 1 – 15
Task 5.2 | Design and fabrication of Si beamshaper | 1 – 30
Task 5.3 | Design and fabrication of passive ultra-compact components as filters | 1 – 15
Task 5.4 | Signal generation module design | 4 – 12
Task 5.5 | Signal Generation Module implementation via FPGA | 13 – 24

## Slide 5: Milestones
 | Names of the Milestones | Month | Partner
MS25 | Decision on optimized plasmonic waveguide couplers | 6 | KIT
MS26 | Fabrication of plasmonic waveguide couplers with less than 3 dB coupling loss | 12 | KIT
MS27 | Design of first generation beam shapers and compact optical filters | 12 | IMEC
MS28 | DDCM with electrical PHY design and verification | 12 | ST
MS29 | Data codecs for power consumption reduction | 15 | ST
MS30 | Decision on plasmonic waveguide couplers with less than 3 dB coupling loss | 15 | KIT
MS32 | Fabrication of compact optical filters and first generation beam shapers | 18 | IMEC
MS33 | Data codecs for error detection and correction | 18 | ST

## Slide 6: Deliverables
 | Names of the Milestones | Month | Partner
D5.1 | DDCM specification document | 6 | ST
D5.2 | DDCM with electrical PHY design and verification data base | 12 | ST
D5.3 | Compact optical filters (2nm bandwidth, >30nm FSR) and first generation beam shapers | 21 | imec
D5.4 | Generic DDCM compatible with plasmonic-based PHY specification document | 24 | ST
D5.5 | Report on plasmonic waveguide couplers | 24 | imec
D5.6 | Generic DDCM compatible with plasmonic-based PHY design and verification data base | 30 | st
D5.7 | Second generation beam shapers (distance 1mm, with bandwidth > 10nm and efficiency > 3dB) | 33 | imec

## Slide 7: Tasks
 | Names of the Tasks | Time Period [months]
Task 5.1 | Modeling and fabrication of coupling Si waveguide to plasmonic waveguide | 1 – 15
Task 5.2 | Design and fabrication of Si beamshaper | 1 – 30
Task 5.3 | Design and fabrication of passive ultra-compact components as filters | 1 – 15
Task 5.4 | Signal generation module design | 4 – 12
Task 5.5 | Signal Generation Module implementation via FPGA | 13 – 24

## Slide 8: Task 5.1 - SPP Excitation in the Slot
q
Reported in MS25 (month 6)
First objective: simulation of optical coupler

## Slide 9: Task 5.1 - Fabrication by KIT & IMEC
Design
Second objective: Optimal coupler fabrication (KIT+imec)

## Slide 10: Task 5.1 - Optical Characterization
Light Coupling Configuration
Cut-back measurement
2dB coupling loss
per tapered coupler!
Reported in MS26 (month 12)

## Slide 11: Tasks
 | Names of the Tasks | Time Period [months]
Task 5.1 | Modeling and fabrication of coupling Si waveguide to plasmonic waveguide | 1 – 15
Task 5.2 | Design and fabrication of Si beamshaper | 1 – 30
Task 5.3 | Design and fabrication of passive ultra-compact components as filters | 1 – 15
Task 5.4 | Signal generation module design | 4 – 12
Task 5.5 | Signal Generation Module implementation via FPGA | 13 – 24

## Slide 12: Task 5.2 – Optical Beam Steerers
Original objective: focusing grating, distance 100mm, 5dB loss (GEN1)
New objective: develop movable gratings
        1 mm movement in plane - 1 degree rotation
Status:
  First generation designed - Fabrication completed
  Characterization on going: 1 mm lateral movement measured

## Slide 13: Tasks
 | Names of the Tasks | Time Period [months]
Task 5.1 | Modeling and fabrication of coupling Si waveguide to plasmonic waveguide | 1 – 15
Task 5.2 | Design and fabrication of Si beamshaper | 1 – 30
Task 5.3 | Design and fabrication of passive ultra-compact components as filters | 1 – 15
Task 5.4 | Signal generation module design | 4 – 12
Task 5.5 | Signal Generation Module implementation via FPGA | 13 – 24

## Slide 14: Task 5.3 – Optical filter
Goal: filter optical amplifier noise before detector
Objective: 3nm bandwidth, 10dB suppression, 30nm FSR
Activities:
Designed different types of filters (AWG, ring)
Fabricated + Characterized filters
100um
AWG
Ring

## Slide 15: Task 5.3 – Optical Filter
Device Details:
10x400 GHz AWG - size: 370x330 um2 - design FSR = 42 nm
Measurement details:
Insertion Loss: -0.90dB Non Uniformity: 0.8 dB
Crosstalk: 22 dB 3dB Bandwidth: 1.75 nm
Standard AWG

## Slide 16: Task 5.3 – Optical Filter
Flat-top AWG
Device Details:
12x400 GHz AWG - size: 560x350 um2 - design FSR = 38.2 nm
Measurement details:
Insertion Loss: 3.29dB Crosstalk: 17 dB 3dB Bandwidth: 3.30 nm

## Slide 17: Task 5.3 – Optical Filter
Double ring
Single ring
3dB Bandwidth = 0.34nm
Crosstalk <-20dB
Size: 25x25 um2
3dB Bandwidth = 1.12nm
Crosstalk <-20dB
Size: 50x25 um2
Reported in MS27 (month 12)
Evaluated different types of filters
Specifications of proposal fulfilled
Ready for integration in demonstrator

## Slide 18: Tasks
 | Names of the Tasks | Time Period [months]
Task 5.1 | Modeling and fabrication of coupling Si waveguide to plasmonic waveguide | 1 – 15
Task 5.2 | Design and fabrication of Si beamshaper | 1 – 30
Task 5.3 | Design and fabrication of passive ultra-compact components as filters | 1 – 15
Task 5.4 | Signal generation module design | 4 – 12
Task 5.5 | Signal Generation Module implementation via FPGA | 13 – 24

## Slide 19: Task 5.4 – Main Achievements
DDCM functional specification completed (D5.1)
DDCM design activity completed (MS28/D5.2)
  VHDL design completed
    All features in place (STNoC support, virtual wires, Qos, credit-based flow control, PHY adapter, electrical PHY)
  Verification environment in place for both VHDL and netlist
  Full regression in place and passing
DDCM design characterization completed
  Area: around 300 Kgates - Speed: up to 450 MHz
  PHY Tx crossing latency: 3.5 cycles at 450MHz
  PHY Rx crossing latency: 0.5 cycles at 450MHz
  Total crossing latency: 4 cycles at 450MHz i.e. 8.88ns
A patent proposal under evaluation by ST patent committee

## Slide 20: Task 5.4 – DDCM Specification
The DDCM is composed of a transmitter (Tx) and a receiver (Rx).
Transmitter:
initiator requests
target responses,
asynchronous events
credit information,
Receiver:
Collecting information from the other die.
Physical channel is unidrectional, two channels ensure the simultaneous communication between the two dice.
D5.1 (month 6)

## Slide 21: Task5.4 – DDCM Specification
Transmitter/Receiver
=
controller + PHY
Controller:
storage FIFOs, QoS and flow control logic,
serialization and frequency conversion modules
PHY:
data transmission at physical level.
D5.2 (month 12)

## Slide 22: Task 5.4 - What’s next
Security encoder
LP encoder
EDC encoder
Serializer
Emitter/
modulator driver
Emitter/
modulator
Security decoder
LP decoder
EDC decoder
Deserializer
TIA
Detector
Traffic source
Traffic Destination
Physical channel (waveguide, fiber, free space)
Digital
Analog
Photonic
New modules to be developed include codecs for data encryption for security, codecs for reducing dynamic power consumption, and codecs for error detection and correction in case of noisy physical channel.

## Slide 23: Summary
Progress fully according to plan
Optical interfaces designed, fabricated and tested
  Coupler dielectric <> plasmonic waveguide
  Optical filters
  Optical beam shapers
Electrical interfaces designed and implemented

## Slide 24: Outlook
Task 5.1 – Couplers
  Further optimization of the process
  Next post-processing is being carried out by KIT
  New cut-back measurement
Task 5.2 – Beam shapers
  Incorporate foucssing grating on moving platform
Task 5.3 – Filters
  Completed
Task 5.4 – DDCM specification
  Completed
Task 5.5 – DDCM implementation
  Signal Generation Module implementation via FPGA

## Slide 25: Task 5.2 – Optical Beam Steerers
Status:
  First generation designed
  Fabrication completed
  Characterisation on going: 1 mm lateral movement measured