## Slide 1
WP-1 Presentation
“NAVOLCHI Management”
Manfred Kohl
Karlsruhe Institute of Technology (KIT), Germany

## Slide 2: Outline
Overview and Project Governance
Resources: Budget and Manpower
Communication: Meetings and Phone Conferences
Management Deliverables
Status of Work: The Project after 1½ Years
Summary

## Slide 3: Overview of WPs

## Slide 4: Management: Main Tasks
Strategic management at project level
Control of work package activities, including technical quality control
Organisation of project reporting and meetings
Control of deliverable preparation
Conflict management

## Slide 5: Project Governance

## Slide 6: General Assembly: Representatives
 | KIT | Manfred Kohl
 | IMEC | Dries Van Thourhout
 | TU/e | Meint Smit
 | AIT | Ioannis Tomkos
 | UVEG | Juan Martinez Pastor
 | ST | Alberto Scandurra
 | Ugent | Zeger Hens
Coordinator (Chair): Juerg Leuthold
+

## Slide 7: Project Management Committee:
WP 1 Leader | KIT | Manfred Kohl
WP 2 Leader | AIT | Emmanouil-Panagiotis Fitrakis
WP 3 Leader | TU/e | Meint Smit
WP 4 Leader | UVEG | Juan Martinez Pastor .
WP 5 Leader | IMEC | Dries Van Thourhout
WP 6 Leader | ST | Alberto Scandurra
WP 7 Leader | AIT | Dimitrios Klonidis
Coordinator: Juerg Leuthold
+
Technical Project Manager (Chair): Manfred Kohl
+
(+ Experts)
(+ Dr. Isaac Suárez)
Manfred Kohl
Jürg Leuthold

## Slide 8
1. Tranche: |  | 1 400 000 € | 58%
 | Total Sum | 58% | 1 Tranche
KIT | 495 615 € | 289 109 € | 290 000 €
IMEC | 386 013 € | 225 174 € | 225 000 €
TU/e | 362 224 € | 211 297 € | 210 000 €
AIT | 304 988 € | 177 910 € | 180 000 €
UVEG | 311 540 € | 181 732 € | 180 000 €
ST | 411 700 € | 240 158 € | 240 000 €
Ugent | 127 920 € | 74 620 € | 75 000 €
 | 2 400 000 € | 1 400 000 € | 1 400 000 €
First payment done
at project start:
A: Actual Costs; T: Transitional Flat Rate
Resources: Budget and Pre-financing
Next payment after
first report period (M18)

## Slide 9: Resources: Budget after Month 18

## Slide 10: Resources: Manpower up to Month 18

## Slide 11: Communication
Meetings:
  Kick-Off in Karlsruhe, Germany
  6-Month Meeting in Warwick, UK
  12-Month Meeting in Ghent, Belgium
  18-Month Meeting in Karlsruhe, Germany
Phone Conferences:
  18 up to now (July 2013), typically monthly
  Topics: Work progress, adjustments, ..
  Presentations documented at WEB-Site

## Slide 12: Time Scale
No problems expected

## Slide 13: Management Deliverables
Deliverables covered by work package 1 with delivery dates are:
 | Names of the Deliverables | Month | Partner
D1.1: | Project web site with .eu domain and continuous update | 1 | KIT
D1.2: | Project reference online manual | 3 | KIT
D1.3: | Project quality assurance manual | 6 | KIT
D1.4: | Intermediate progress report (1) containing work progress and management activities up to month 9 07/2012 | 9 | KIT
D1.5: | Intermediate Progress Report | 27 | KIT
All have been prepared in time

## Slide 14: Status: Deliverables
All deliverables finished in time
Next deliverable in M21 (July 2013)
No critical status level expected

## Slide 15: Status: Milestones (already reviewed)
Presented in review 1 (November 2012)
All milestones finished in time

## Slide 16: Status: Milestones
MS46:
Delayed due to management restructuration within ST
MS13:
Obsolete due to revised MS plan
Next milestones in M21 (July 2013)
No further critical status level expected

## Slide 17: Summary
Project Structure
Partner Communication
Resources
Technical and Scientific Progress
Dissemination

## Slide 18
Thank you!

## Slide 19: Budget KIT

## Slide 20: Budget IMEC

## Slide 21: Budget TUe

## Slide 22: Budget AIT

## Slide 23: Budget UVEG

## Slide 24: Budget ST

## Slide 25: Budget UGent