## Slide 1
Work Package 3: Plasmonic Transmitter
Victor Dolores-Calzadilla, Meint Smit
Eindhoven University of Technology (TU/e), The Netherlands

## Slide 2: Outline
WP3 Position in Project
Objectives
Tasks
Milestones and Deliverables
Status of Work
  Plasmonic/Metallic Laser
  Plasmonic Modulator
Summary and Outlook

## Slide 3: WP3 Position in Project
Contributors:

## Slide 4: Objectives
Simulation studies
  Plasmonic/metallic nanolaser
  Plasmonic modulator
Fabrication
  Electrically pumped plasmonic/metallic nanolaser
  Electrically driven plasmonic modulator
Performance targets
  Laser: active region < 1 mm2, output power > 100 mW
  Modulator: extinction ratio > 3dB for length < 10 mm, and a total modulation speed > 40 Gbit/s

## Slide 5: Tasks
 | Names of the Tasks | Time Period [months]
Task 3.1 | Modelling of plasmonic laser and optimization of bonding technology | 1 – 6
Task 3.2 | Modelling of plasmonic modulator | 1 – 18
Task 3.3 | Fabrication of plasmonic/metallic nanolaser | 7 – 30
Task 3.4 | Fabrication of Si-plasmonic modulators | 7 – 27

## Slide 6: Milestones
 | Names of the Milestones | Month | Partner
MS8 | Decision on an optimized structure for metallic/plasmonic nanolaser and its coupling to a Si-waveguide | 6 | TU/e
MS9 | Decision on an optimized structure for plasmonic modulator | 6 | KIT
MS10 | Grown wafer structure for plasmonic lasers | 12 | TU/e
MS11 | Fabrication of plasmonic modulator on a SOI platform | 15 | KIT
MS12 | Decision on an optimized structure for plasmonic modulator with a maximum loss of 20dB | 18 | KIT
MS13 | Initial characterization of unbonded plasmonic lasers | 18 | TU/e
MS14 | Initial testing and characterization of plasmonic modulators | 21 | KIT
*MS15 | Initial testing of bonded plasmonic lasers | 24 | TU/e
*MS15 to be updated after demonstration of nanolaser

## Slide 7: Deliverables
 | Names of the Deliverables | Month | Partner
D3.1 | Report on studies of optimized structure for metallic/plasmonic nanolaser and its coupling to Si-waveguide | 12 | TU/e
D3.2 | Report on modelling of the modulator structure | 12 | KIT
*D3.3 | Fabrication of plasmonic laser device | 24 | TU/e
D3.4 | Report on fabrication of modulators | 24 | KIT
*D3.3 to be updated after demonstration of nanolaser

## Slide 8: Metallic/Plasmonic Laser Approaches
Fabry-Perot plasmonic laser [1]
  High propagation loss and poor active confinement
Reported in MS8 & D3.1
xy
|E|2
|E|2
[1] V. Dolores-Calzadilla, et al., Towards plasmonic lasers for optical interconnects, ICTON 2012.
[2] V. Dolores-Calzadilla, et al., Waveguide-coupler nanolasers in III-V membranes on silicon , ICTON 2013.
Metallo-dielectric nanolaser [2]

## Slide 9
Optical and electrical optimization
Direct modulation (small signal response)
Q ~ 530 @ 1.55 µm
Threshold gain ~ 800 cm-1
Threshold current ~ 120 µA
Differential efficiency ~ 0.16
Output power ~ 40 µW @ 420 µA (2V)
Task 3.1 Modelling of the Nanolaser
Periodic report (M1-M18)
  fc > 60 GHz
  for Pout = 50 µW

## Slide 10: Task 3.3 Fabrication of the Nanolaser
Low-loss low-resistance Ge/Ag ohmic contacts [1]
Reported in D6.1
[1] L. Shen, V. Dolores-Calzadilla, et. al., Journal paper to be submitted
InGaAs (N>1x1019 cm-3): , 2nm Ge @ 350C
InP (N~2x1018 cm-3) [1] : , 30nm Ge @ 400C

## Slide 11
Main fabrication issues
  Outgassing during annealing
  From dummy to real fabrication
Task 3.3 Fabrication of the Nanolaser
Ag
  Typical defects at T>300C
  Outgassing minimized by using thick bonding layer
  Pure InP wafer
  III-V layer stack bonded to silicon

## Slide 12: Task 3.3 Fabrication of the Nanolaser
Current fabrication of 2nd run (75% progress)
Reported in D6.1
Q
InP
Grating coupler
Interface from Q/InP to InP waveguide
Pillar cavity
  Critical step: outgassing during silver annealing

## Slide 13: Another Relevant Device
Metal grating coupler [1,2]
[1] V. Dolores-Calzadilla, D. Heiss, M. Smit, Optics Letters 39, 9 (2014).
[2] V. Dolores-Calzadilla, A. Higuera Rodriguez, D. Heiss, USA Provisional patent application filed (2014).
Performance independent from buffer thickness
Enables high yield (thick) polymer bonding
Reduce optical parasitics into buffer/substrate
First run:
6 dB loss @ 1550nm

## Slide 14: Summary and Outlook (Laser)
  Summary
    Modelling of metal-cavity nanolasers
    Growth of III-V wafers and improvement of bonding to Si substrates
    Technology development was carried out of (1) low-loss low-resistance Ge/Ag contacts with , and (2) lithographic and etching processes for the nanolaser (2nd run currently under fabrication)
    An additional relevant device was proposed: metal grating coupler
  Outlook
    Finish 2nd run of nanolasers
    Carry out the characterization of the integrated nanolasers

## Slide 15: Long-term Outlook (Laser)
  Classical lasers are not suitable for low power operation
    Relatively high threshold currents
    Low wall plug efficiency at low power levels
    Limited direct modulation speed
  Nanolasers
    Combine low threshold currents with high direct modulation speed
    Wall plug efficiency still requires improvement
    Particularly promising in combination with receiverless transmission (small capacity detectors)

## Slide 16: Plasmonic Modulator Approaches
Reported in MS9 & D3.2
SPP absorption modulator
SPP phase modulator

## Slide 17
Task 3.4 Fabrication of the Modulator
Performance
      Extinction ratio: 6 dB
      Length: 5 µm
      Operating voltage: 4 V
      Energy consumption: 76 fJ / bit
      Speed: MHz
Bottom
contact
Top
contact
5 µm long plasmonic switch
C. Hoessbacher, Y. Fedoryshyn, A. Emboras, A. Melikyan, M. Kohl, D. Hillerkuss, et al., "The plasmonic memristor: a latching optical switch," Optica, vol. 1, pp. 198-202, 2014/10/20 2014.
Reported in D6.1

## Slide 18
Task 3.4 Fabrication of the Modulator
A. Melikyan et al., "High-speed plasmonic phase modulators," Nature Photon. 8(2), 229–233 (2014).
Passive silicon-on-insulator (SOI) wafer processing
E-beam lithography for defining 140 nm wide slot in gold
Coating with an electro-optic polymer
  M3 (r33 = 70 pm/V) [GigOptix]
  SEO100 (r33 = 110 pm/V) [Soluxra]
  YLD/PSLD (r33 = 230 pm/V) [Larry Dalton, UW]
Poling of electro-optic polymer with static electric field
Reported in MS11

## Slide 19
Vm = 0.8 V
r33 ≈ 21 pm / V
VpL = 1.3 Vmm
Vm = 0.1 V
A. Melikyan et al., "High-speed plasmonic phase modulators," Nature Photon. 8(2), 229–233 (2014).
Task 3.4 Fabrication of the Modulator
65 GHz RF bandwidth (lc = 1.55mm)
Broadband optical operation across 120nm (fm = 45GHz)
Characterization results

## Slide 20
Task 3.4 Fabrication of the Modulator
Experimental setup for 200 nm slot modulator with M3-Gig (1stG)
Constellation diagrams (BER ≈ 10-3)
20dBm
Vm = 7.5 Vpp
Dj = 0.23rad

## Slide 21
Task 3.4 Fabrication of the Modulator
Experimental setup for 140 nm slot modulator with YLD / PSLD (3rdG)
Vm ~ 4 Vpp
Dj ~ 1.46rad
Constellation diagrams (BER < 10-10)
10dBm

## Slide 22
Task 3.4 Fabrication of the MZM
OOK signaling up to 40Gbit/s

## Slide 23: Summary and Outlook (Modulator)
  Summary
    Modelling of plasmonic modulators
    Plasmonic phase and Mach-Zehnder modulator has been successfully demonstrated
Bandwidth > 65 GHz
Broadband optical operation: Dl > 120 nm
VpL = 0.5 Vmm
Length: 29 mm
    Reliable operation at 85˚ C
Insertion loss (incl. transitions): 12…14 dB
  Outlook
    Bandwidth improvements of the absorption modulator
    BER improvement of the Mach-Zehnder modulators (MZMs)
    Fabrication of an array of MZMs
  Application areas
    Short-reach interconnects
    WDM backbone (WDM + QAM formats + high symbol rates)