## minutes of meeting
Minutes of NAVOLCHI Meetings and Conference Calls
Phone Conference | Item No. | Contents | Type | Resp. | Concerning | Due date | Status | Result | Open issues | Close date
3 | 0 | Date: 12.03.2012 4pm Title: Navolchi Telephone Conference 03 Consortium Institutions: KIT, IMEC, TU/E, AIT, UVEG, UGent, STi Institutions are represented by: (KIT) Dr. Martin Sommer, Dr. Manfred Kohl, Sascha Mühlbrandt (IMEC) Prof. Dries Van Thourhout (TU/E) Prof. Meint Smit, Victor Dolores-Calzadilla , Andrea Fiore (AIT) Prof. Ioannis Tomkos, Dr. Emmanouil-Panagiotis Fitrakis (UVEG) Prof. Juan Martinez Pastor (UGent) Prof. Zeger Hens (STi) Dr. Alberto Scandurra, Eloisa Catania, Anna Muscarà | I
3 | 1 | New ST team: Introduction (See introductory slides on NAVOLCHI-website) | I
G. Catania and A. Muscara from ST are new members contributing to NAVOLCHI Support to all the partners for designing, manufacturing, testing and characterizing plasmonic devices Realization and characterization of a demonstrator oriented to SiP applications Benchmarking of plasmonics based solution versus alternative solutions
3 | 2 | Consortium Agreement | I
ST signed Consortium agreement just today(12/03/2012). Consortium agreement is now signed by all members and complete.
Dr. Martin Sommer(KIT) asks the General Assemby for a change of the consortium agreement with respect to a shorter period for publication of abstracts to a specified set of conferences as described in the preliminary version of the Quality Assurance Manual, which is available on the NAVOLCHI-web-site. No decision made during the conference call.
3 | 3 | Progress Reports (See NAVOLCHI-website for slides with detailed information) | I
|  | KIT: 'Qualitiy assurance Manual' prerelease on NAVOLCHI website |  |  | WP1
|  | AIT: Work on Plasmonic Amplifier simulation concerning better efficiency and higher accuracy. Several dissemination programs ongoing. Additional dissemination plans concern papers on loss enabled nonlinear plasmonic phenomena. Publication is paper with Valenzia on Surface plasmon amplifiers |  |  | WP4, WP7
|  | IMEC: FDTD Simulation of amplifier is near to completion Further work concerns the electrical injection into the device and the local deposition of QDs |  |  | WP4
|  | UGENT: Progress made in QD processing and characterization of QD optical properties |  |  | WP4
|  | ICMUV: Work on planar Plasmonic Waveguides and synthesys of Quantum-Dots for infrared PD |  |  | WP4
|  | TU/e: Design of Plasmonic Laser Optical and electrical properties simulations |  |  | WP3
|  | ST: Report on chip-to-chip interconnect requirements and needs completed First draft of DDCM functional specification completed |  |  | WP2
3 | 4 | ST: DDCM architecture definition / Consortium member feedback | I
High-level DDCM layout is accepted. Until the next Conference Call detailed interconnect parameters between the electrical components and the plasmonic/optical components shall be defined (e.g. voltage and current levels, bandwidth, power consumption).
3 | 5 | Appointment for next Consortium Meeting July 2012 | D
AIT prepares Navolchi-Session for ICTON conference in Warwick/UK. Suggests to conduct next meeting after ICTON at a local site (hotel or conference rooms) on July 6th, 2012. Another possibility is Gent, with more freedom concerning the exact date. No decision made during the conference call DOODLE-Request will be issued by Dr. Martin Sommer(KIT) about place and date of next meeting.
3 | 6 | Intermediate report scheduled for July 2012 | D
Input from every partner is needed until June 2012
3 | 8 | Next Telephone Conference | D
Monday, April 2nd. 4pm