## minutes of meeting
Minutes of NAVOLCHI Meetings and Conference Calls
Phone Conference | Item No. | Contents | Type | Resp. | Concerning | Due date | Status | Result | Open issues | Close date
4 | 0 | Date: 02.04.2012 4pm Title: Navolchi Telephone Conference 04 Consortium Institutions: KIT, IMEC, TU/E, AIT, UVEG, UGent, ST Institutions are represented by: (KIT) Prof. Juerg Leuthold, Dr. Martin Sommer, Dr. Manfred Kohl, Argishti Melikyan, Sascha Mühlbrandt (IMEC) Prof. Dries Van Thourhout (TU/E) Victor Dolores-Calzadilla , Andrea Fiore (AIT) Prof. Ioannis Tomkos, Dr. Emmanouil-Panagiotis Fitrakis (UVEG) Prof. Juan Martinez Pastor (UGent) Prof. Zeger Hens (ST) Eloisa Catania, Anna Muscarà | I
| 1 | Progress Reports | I
KIT: Comparison of Absorption Modulator and Phase Modulator, Optimized Couplers
TU/e: Comparison of two Plasmonic Laser Structures Additional time needed (2-3 weeks) to decide on particular approach for device structure and accomplish Milestone MS8, scheduled for April 2012
AIT: NAVOLCHI Brochure Draft, Simulation of Amplifier with UVEG, Doodle Request for upcoming Phone Conference for definition of Device Specifications (compare Item No.4)
UVEG: Measurement of Gain for Planar Waveguides, New Amplifier Designs
UGent Quantum Dot Amplifiers: Pump-Probe Measurements performed on QD, Photo induced Intraband Absorption opposes gain
| 2 | Allocation of Next In Person Meeting | D
The participants of the Phone Conference agreed on meeting after ICTON - WARWICK/UK since there is already a NAVOLCHI session organized. Meeting will be held on July, 6th 2012.
| 3 | Dissemination of NAVOLCHI Results | I | AIT | WP7
There will be a survey paper by OPN about Plasmonics. Consortium members are invited to contribute with NAVOLCHI-related articles. Editor and Contact is Juerg Leuthold(KIT). Contributions have to be filed within the next six month.
| 4 | Definition of DDCM Architecure: Additional Phone Conference | D
Additional Phone Conference is shifted. New Doodle request is set up to allocate appointment: http://www.doodle.com/rwngkuiq2wv58mk2
| 5 | Upcoming Milestones April 2012 | I
AIT: MS2 TU/e: MS8 KIT: MS9, MS25
| 6 | Reminder: Intermediate Progress Report July 2012 | I
Input from every partner needs to be filed in JUNE 2012
| 7 | Next regular Telephone Conference | I
Monday, May the 7th, 4pm