## minutes of meeting
Minutes of NAVOLCHI Meetings and Conference Calls
Phone Conference | Item No. | Contents | Type | Resp. | Concerning | Due date | Status | Result | Open issues | Close date
5 | 0 | Date: 07.05.2012 4pm Title: Navolchi Telephone Conference 05 Consortium Institutions: KIT, IMEC, TU/E, AIT, UVEG, UGent, ST Institutions are represented by: (KIT) Prof. Juerg Leuthold, Dr. Martin Sommer, Dr. Manfred Kohl, Argishti Melikyan, Sascha Mühlbrandt (IMEC) Prof. Dries Van Thourhout, Dr. Kasia Komorowska,Sukumar Rudra (TU/E) Prof. Meint Smit, Victor Dolores-Calzadilla , Andrea Fiore (AIT) Prof. Ioannis Tomkos, Dr. Emmanouil-Panagiotis Fitrakis (UVEG) Prof. Juan Martinez Pastor, Dr. Isaac Suárez Álvarez (UGent) Prof. Zeger Hens (ST) Alberto Scandurra | I
| 1 | Progress Reports | I
KIT: Phase Modulator Specifications and Requirements (ST response to requirements: 4.5V Peak-to-Peak operating Voltage is achievable)
TU/e: Coupling Schemes of Plasmonic Laser, Milestone MS8 postponed by 1 Month
AIT: Amplifying Insulator-Metal-Insulator waveguides: Plasmonic Properties, Information on ICTON 2012
UVEG: Dielectric and Plasmonic CdSe-PMMA waveguides
IMEC/UGent Beam Steering with movable grating coupler on MEMS platform, Amplifier current injection
ST: Main Achievements
| 2 | ICTON 2012 Navolchi Session and Consortium Meeting | I
No official schedule yet, but NAVOLCHI Session is planned to take place on the morning of July, 5th
| 3 | Upcoming Milestones | I
Milestone MS8 (responsible Partner: TU/e) is delayed by one month, AIT asks all Consortium Partners to submit device specifications for MS2 by May, 14th , Preliminary Versions of Milestones MS2, MS9 and MS25 can be accessed on the NAVOLCHI website
| 4 | Reminder: Intermediate Progress Report July 2012 | I
Input from every partner needs to be filed in JUNE 2012
| 5 | Next regular Telephone Conference | I
Monday, June the 4th, 4pm