## minutes of meeting
Minutes of NAVOLCHI Meetings and Conference Calls
Phone Conference | Item No. | Contents | Type | Resp. | Concerning | Due date | Status | Result | Open issues | Close date
7 | 0 | Date: 03.09.2012 4pm Title: Navolchi Telephone Conference 07 Consortium Institutions: KIT, IMEC, TU/E, AIT, UVEG, UGent, ST Institutions are represented by: (KIT) Dr. Manfred Kohl, Argishti Melikyan (IMEC) Prof. Dries Van Thourhout (TU/E) Victor Dolores-Calzadilla (AIT) Dr. Emmanouil-Panagiotis Fitrakis (UVEG) Prof. Juan Martinez Pastor, Dr. Isaac Suárez Álvarez (UGent) Prof. Zeger Hens (ST) Alberto Scandurra | I
| 1 | Progress Reports | I
KIT: Device fabrication of Plasmonic Modulator: Optimization of Silicon etching process Fabrication of array of devices characterization of propagation and coupling losses.
TU/e: Metallo-Dielectric Nanolaser: Dosis tests SiO2 roughness measurement Pillar etching Wet etching
AIT: Ongoing amplifier simulation White Paper on Plasmonic Interconnect innovation in progress
UVEG: Model to fit experimental data of gain curve Dielectric and Plasmonic Waveguides using QRs from Ugent New plasmonic waveguide designs
IMEC WP4: Characterisation of interaction QDOTS with silicon waveguide WP4: Build proposed amplifier with improved top contacts WP4: Etching tests SiN-films with embeddd QDOTS ongoing WP5: Second gen passive filter WP5: Steerable gratings
UGENT: Absorption enhancement in QD monolayers Intraband absorption with PbX QDs Pump-probe measurements -> amplification Absorbance of functionalized waveguides
ST: DDCM design activity completed VHDL design completed Verification environment in place for both VHDL and netlist Full regression in place and passing Architectural enhancement completed
| 2 | Inconsitencies in DoW and other official documents | I
The list of deliverables in the DoW has some inconsistencies that need to be corrected. The name of IMEC is wrong in the documents (DoW, intermediate progress report, others). All Partners will be asked via E-Mail to look for and notify about all inconsitencies in the project's documents. These will be removed where possible.
| 3 | Next In-Person meeting | I
The partners wish that the NAVOLCHI meetings should be in different locations. Instead of KIT also U Gent or ST Microelectronics have been suggested for our next meeting. Possible dates are in the beginning/middle of November. Actions: - The location should be clarified - The organizing Partner should conduct a doodle request to settle an appointment.
| 4 | Next regular Telephone Conference | I
Monday, October 8th, 4pm