## minutes of meeting
Minutes of NAVOLCHI Meetings and Conference Calls
Phone Conference | Item No. | Contents | Type | Resp. | Concerning | Due date | Status | Result | Open issues | Close date
8 | 0 | Date: 08.10.2012 4pm Title: Navolchi Telephone Conference 08 Consortium Institutions: KIT, IMEC, TU/E, AIT, UVEG, UGent, ST Institutions are represented by: (KIT) Dr. Martin Sommer, Dr Manfred Kohl Argishti Melikyan, Sascha Mühlbrandt (IMEC) Prof. Dries Van Thourhout (TU/E) Victor Dolores-Calzadilla (AIT) Dr. Emmanouil-Panagiotis Fitrakis (UVEG) Dr. Isaac Suárez Álvarez (UGent) Prof. Zeger Hens (ST) Alberto Scandurra | I
| 1 | Progress Reports | I
KIT: Optical characterization of phase modulators, transmission experiments and estimation for the coupling losses. MS26 on time.
TU/e: Process flow for the metallo-dielectric laser.
AIT: Dissemeniation activities D2.2 is due end of October. Partners are asked for input. Suggest to merge SOFI and NAVOLCHI summer school in summer 2012.
UVEG: Progress on Plasmonic Amplifiers and Detector. MS16 on time.
IMEC: MEMS based steerable gratng couplers Electrically injected Silicon quantum-dot amplifiers Optimization of SiN etching process Characterization of 1D photonic crystal structures in Silicon
UGent: Absorption enhancement in QD monolayers Absorbance of functionalized waveguides
ST: DDCM design characterization in progress Identified DDCM modifications required for matching project targets
| 2 | Reminder: Several Milestones are due end of October! Please submit in time! | I
| 3 | Organization of Consortium Meetings in Gent and Brussels | I
The KIT proposed to have two distinct meetings with considerrable time in between such that the Brussels review meeting can be discussed. UVEG, AIT and ST stated to favorize a combined meeting. Issue needs to be discussed again. No dates were fixed.
| 4 | Next Telephone Conference | I
November 5th, 2012 4pm