## minutes of meeting
Minutes of NAVOLCHI Meetings and Conference Calls
Phone Conference | Item No. | Contents | Type | Resp. | Concerning | Due date | Status | Result | Open issues | Close date
11 | 0 | Date: 17.12.2012 4pm Title: Navolchi Telephone Conference 11 Consortium Institutions: KIT, IMEC, TU/E, AIT, UVEG, UGent, ST Institutions are represented by: (KIT) Dr. Martin Sommer, Dr Manfred Kohl Argishti Melikyan, Sascha Mühlbrandt (IMEC) Prof. Dries Van Thourhout (TU/E) Victor Dolores-Calzadilla (AIT) Dr. Emmanouil-Panagiotis Fitrakis (UVEG) Dr. Isaac Suárez Álvarez (UGent) Prof. Zeger Hens (ST) Alberto Scandurra | I
| 1 | Progress Reports | I
Reports available on NAVOLCHI website
| 2 | Discussion about review meeting in Brussels | I
Reviewers happy with innovaion potential and devices. -> Demonstration of system will be challenge of the project -> WP2 has to be improved -> Numbers for speed, crosstalk and power consumption should be assessed. Respective deliverable will be revised until June (next Review meeting)
| 3 | System approach and Contingency Plan | I
IMEC might have some existing chip designes available for receiver part. Detectors on chip might work up to 10G
| 4 | Optics and Photonics Article
Article for OPN: Opportunity to spread idea of NAVOLCHI. Partners agree contributing: AIT: Motivation and Wavegudies KIT: Modulators UVEG: Receiver TU/e will be asked for laser source part
| 5 | Next Telephone Conference | I
January 14th, 2013 4pm