## minutes of meeting
Minutes of NAVOLCHI Meetings and Conference Calls
Phone Conference | Item No. | Contents | Type | Resp. | Concerning | Due date | Status | Result | Open issues | Close date
13 | 0 | Date: 04.02.13 4pm Title: Navolchi Telephone Conference 13 Consortium Institutions: KIT, IMEC, TU/E, AIT, UVEG, UGent, ST Institutions are represented by: (KIT) Dr Manfred Kohl, Dr. Martin Sommer, Argishti Melikyan, Sascha Mühlbrandt (IMEC) (TU/E) Victor Dolores-Calzadilla (AIT) Dr. Emmanouil-Panagiotis Fitrakis (UVEG) Dr. Isaac Suárez Álvarez (UGent) (ST) Alberto Scandurra | I
| 1 | Progress Reports | I
Reports available on NAVOLCHI website / Zeger and Dries not available this time
| 2 | Discussion about Contingency Plan | I
Next opportunity for fabrication of Ge-Detectors on Chip is 2014 Chips with 35µm pitch already exist at IMEC -> change to 35µm distance between each channels this change has been approved by all partners present
| 3 | Upcoming Consortium Meeting in Brussels | I
Scheduling Brussels meeting 10th of July: No objections from partners.
| 4 | Next Telephone Conference | I
March 4th, 2013 4pm