## minutes of meeting
Minutes of NAVOLCHI Meetings and Conference Calls
Phone Conference | Item No. | Contents | Type | Resp. | Concerning | Due date | Status | Result | Open issues | Close date
14 | 0 | Date: 04.03.13 4pm Title: Navolchi Telephone Conference 14 Consortium Institutions: KIT, IMEC, TU/E, AIT, UVEG, UGent, ST Institutions are represented by: (KIT) Dr. Martin Sommer, Dr Manfred Kohl, Sascha Mühlbrandt (IMEC) Prof. Dries Van Thourhout (TU/E) Victor Dolores-Calzadilla (AIT) Dr. Emmanouil-Panagiotis Fitrakis (UVEG) Dr. Isaac Suárez Álvarez (UGent) Prof. Zeger Hens (ST) Alberto Scandurra | I
| 1 | Progress Reports | I
Reports available on NAVOLCHI website
| 2 | Discussion concerning Contingency Plan | I
Ge detectors available from IMEC: 30-40GHz bandwidth, efficiency 0.5A/W 35µm pitch Detectors can be used in NAVOLCHI, but IMEC should be on all publications where they will be used -> Claudia Hoessbacher will develop a schedule for the contingency plan for the upcoming months
| 3 | Current issues related to the project | I
ST is currently being restructured. Some milestones of ST can not be fulfilled anymore. Partners need to help out. Sample exchange between Ugent and UVEG has been halted as there is a contradiction in gain measurements. ->An additional phone conference between Gent and Valencia will be scheduled. TU/e wants to merge MS13 and MS15. The EU-Commisioner has to be contacted to initiate the merge.
| 4 | Next Telephone Conference | I
April 1st, 2013 4pm