## minutes of meeting
Minutes of NAVOLCHI Meetings and Conference Calls
Phone Conference | Item No. | Contents | Type | Resp. | Concerning | Due date | Status | Result | Open issues | Close date
15 | 0 | Date: 08.04.13 4pm Title: Navolchi Telephone Conference 15 Consortium Institutions: KIT, IMEC, TU/E, AIT, UVEG, UGent, ST Institutions are represented by: (KIT) Dr. Martin Sommer, Dr Manfred Kohl, Sascha Mühlbrandt (IMEC) Prof. Dries Van Thourhout (TU/E) Victor Dolores-Calzadilla (AIT) Dr. Emmanouil-Panagiotis Fitrakis (UVEG) Dr. Isaac Suárez Álvarez (UGent) Prof. Zeger Hens (ST) Alberto Scandurra | I
| 1 | Progress Reports | I
Reports available on NAVOLCHI website
| 2 | Merger of MS13 and MS15 | I
Tue wants MS13 and MS15 merged. This will either be explained in MS13 document or in a document of it's own.
| 3 | ST restructuring | I
ST is currently being restructured. This will mean only a delay, but no drop of activities.
| 4 | Exploitation activities
AIT asks for input with respect to industrial outreach and exploitation activities.
| 5 | Next Telephone Conference | I
April 1st, 2013 4pm