## minutes of meeting
Minutes of NAVOLCHI Meetings and Conference Calls
Phone Conference | Item No. | Contents | Type | Resp. | Concerning | Due date | Status | Result | Open issues | Close date
16 | 0 | Date: 13.05.13 4pm Title: Navolchi Telephone Conference 16 Consortium Institutions: KIT, IMEC, TU/E, AIT, UVEG, UGent, ST Institutions are represented by: (KIT) Dr. Martin Sommer, Dr Manfred Kohl, Sascha Mühlbrandt (IMEC) Prof. Dries Van Thourhout (TU/E) Victor Dolores-Calzadilla (AIT) Dr. Emmanouil-Panagiotis Fitrakis (UVEG) Dr. Isaac Suárez Álvarez (UGent) Prof. Zeger Hens (ST) Alberto Scandurra | I
| 1 | Progress Reports | I
Reports available on NAVOLCHI website
| 2 | Other | I
AIT asks partners to submit the respective contributions to D7.1 UVEG: MS20 is nearly done and they will continue with both detector types (Photoconductive/Schottky)
| 3 | Next Telephone Conference | I
June 17th, 2013 4pm