## Slide 1
NAVOLCHI - Nano Scale Disruptive Silicon-Plasmonic Platform for Chip-to-Chip Interconnection

## Slide 2
AGENDA

## Slide 3: Agenda
Welcome.
Progress of work: Short report from every partner about status of work.
Actual deliverables and milestones.
18 month periodic report
Brussels meeting
Open issues.
Next TelConf.

## Slide 4
Status of Work:
Partner Presentations
Notes: Partner presentations (10min each)
  Institute / company (short)
  Contribution to the project, own work effort and timeline (focus)

## Slide 5
  If appropriate: Discussion
  Deliverables & Milestones

## Slide 6: April Deliverables

## Slide 7: January and April Milestones

## Slide 8
Financials
 | actual claimed costs Reporting Period M1 – M18 | planned costs Funding Period 1 M1 – M18 | actual requested funding Funding Period 1 M1 – M18 | planned requested funding Funding Period 1 M1 – M18
KIT |  | 287 807.50 € | 290 000.00 € | 287 807.50 €
IMEC |  |  |  | 
TU/e (a) | 181 645.39 € | 238 877.00 € | 138 620.25 € | 179 157.75 €
AIT | 115 425.00 € | 158 704.00 € | 88 302.00 € | 121 411.00 €
UVEG | 194 466 74 € | 215 000.00 € | 148 48.21 € | 161 250.00 €
ST |  |  |  | 
UGent |  |  |  | 
?

## Slide 9: 18 months periodic report
Missing: Financials  IMEC, ST Ugent; man power  ST, Ugent „Besides the electronic submission, Forms C as well as certificates
(if applicable), have to be signed and sent in parallel by post.“
Please check with your financial staff
Next steps:
Internal revision: Comments until Thursday 20th.
All deliverables, milestones and the report should be sent to the EC and the reviewers until Wednesday 26th.

## Slide 10: Brussels preparation
Next (additional) phone conferences:
June 24th ?
July 1st
Pre-meeting July 9th 1:30 pm in Brussels

## Slide 11: Preparation Meeting July, 9th
Where:
Helmholtz Association of German Research Centres e.V. Brussels Office, Rue du Trône 98 1050 Brussels, BELGIUM
~15 min. from train station Midi via Metro
~1h from Brussels airport via bus or train
When:
1.30pm – 5.30pm
Office closes after 5.30, no extension possible. Please be on time

## Slide 12: Preparation to Brussels
Important topics to prepare:
18 month periodic report
Brussels presentation
  Work progress
  Reaction on reviewers recommendations
Separate documents with reactions on reviewers comments

## Slide 13: Reviewers Comments: Responsibilities
AIT
AIT/KIT
AIT/ST
AIT
IMEC/UVEG
Recommendations concerning the period under review

## Slide 14: Reviewers Comments: Responsibilities
Recommendations concerning future work
J. L.
KIT
KIT

## Slide 15
  Open Issues
  Next Tel. Conf.

## Slide 16: Open Issues
Any important things to discuss?

## Slide 17: Next Phone Conference
July 1st, 2013
First Monday of the next month,
4:00 pm (CET)

## Slide 18
  Bye!