## Slide 1: STMicroelectronics Progress Report

## Slide 2: Recent progress
Completed digital building-blocks design and verification
Completed plasmonic interconnect models and verification
In order to simplify and speed up FPGA mapping, instead of the whole system (two DDCM modules) only PHY Adapter will be mapped and driven from external sources

## Slide 3: NAVOLCHI demonstrator implementation (1/2)
Bi-synchronous FIFO
90
89
4
Ser
FPGA
Driver
4
Plasmonic modulators
4
Light beams
Plasmonic LASERs
Board
OBI Enc
BI
Enc
3
89
Optical Bus Inverter (OBI) Encoder minimizes the number of ones in 89 bits data word in order to reduce the number of LASERs turned on
Bus inverter (BI) encoder minimizes the Hamming distance between back to back 4 bits data words in order to minimize the switching activity of each LASER

## Slide 4: NAVOLCHI demonstrator implementation (2/2)
4
Comparators
4
TIAs
4
Light beams
Plasmonic detectors
Board
Bi-synchronous FIFO
90
89
Des
FPGA
OBI Dec
BI Dec
3
89

## Slide 5: VHDL Models of Plasmonic Devices
TIA
Plasmonic Photodetector
Plasmonic Waveguide
Laser
ModulatorDriver
Plasmonic
Amplifier
CMOS
0/1
Current
Optical
Power
Optical
Power
Optical
Power
Current
0/1
4
4
4
4
4
4
4
‘
,G(<1)
G(>1)
’1’
’0’
’U’

## Slide 6: Short term plan
Full verification of VHD building-blocks and plasmonic component models (this week)
Synthesis for FPGA of all VHDL building-blocks (this and next week, delayed for some HW failures)
Deliverables (D5.4) and milestones (M34) forecasted for end of October suffered of some delay, related documents will be delivered within this week

## Slide 7: Issues
ISG (Interconnect Systems Group) has been closed and all its resources have been moved to MCD (Micro Controller Division)
MCD has no interest in NAVOLCHI project, nevertheless ST doesn’t want to leave the project at this stage
MCD can guarantee only the completion of the digital parts design and the FPGA mapping, while board design and implementation for demonstrator cannot be carried out
  Activity and related budget has to be moved to another partner
Not possible to attend the meeting in Eindhoven for heavy cost reduction