## minutes of meeting
Minutes of NAVOLCHI Meetings and Conference Calls
Meeting | Item No. | Contents | Type | Resp. | Concerning | Due date | Status | Result | Open issues | Close date
| 0 | Date: 02.03.2015 4pm Title: Navolchi Conference Call Consortium Institutions: KIT, IMEC, TU/E, AIT, UVEG, UGent, STi, ETH | I
| 1 | Technical Presentations and Upcoming EC Documents | D
Special Information: 1.) Laser not fully operational until end of the Project: Continue with Contingency plan 2.) ETH plans first test demo of interconnect board in May 2015 IMEC looks for new set of photodiodes with appropriate pitch for the demonstrator 3.) AIT asks for information about optical interconnect roadmap 4.) MS 35 should be submitted by IMEC soon as possible (due time: month 39) 5.) MS 36 belongs to WP5 (WP leader IMEC). As ST is no longer responsible for this task, the report cannot be provided. 6.) MS 39: TU/E will provide updated information on the laser (including pulse shape) to AIT, who will take this information into account in the final version (to be submitted as soon as possible, due time: month 40) 7.) MS 40: TU/E will include the outcome of laser characterization (to be submitted as soon as possible, due time: month 39) 8.) MS 50: Decision on the development of an additional demonstrator besides the contingency plan by AIT and ETH on the basis of the new laser results. No direct modulated laser will be available for the demonstrator (to be submitted in March, due time: month 41) 9.)MS 51: report on the improved metal grating coupler by TU/E (to be submitted in March, due time: month 41)
| 2 | Administration
|  | 1.) Final report: The first draft of reports from the different WPs is expected by July 1st. 2.) Final review meeting: The timeline of demonstrator development suggests that the meeting should be preferably after the end of the project, most probably in September due to summer holidays. | D
| 3 | Next telco
April 13th 2015, 4 pm